## MVP Backlog
ID | Epic | Scope | Priority | Target | Dependencies | Acceptance Criteria | Owner
EP-01 | Foundation & Security | Tenant/org model, environments, CI/CD, secrets, logging, RBAC skeleton | P0 | Sprint 1-2
EP-02 | Identity | SSO/MFA, users, roles, scopes, sessions | P0 | Sprint 1-2
EP-03 | Master Data | Org hierarchy, branches, departments, audit types/templates | P0 | Sprint 2-3
EP-04 | Audit Universe | Universe CRUD, hierarchy, risk/control links, audit history | P0 | Sprint 3-4
EP-05 | Risk Engine | Risk factors, scoring methodology, assessment, approval, heatmap | P0 | Sprint 4-5
EP-06 | Annual Planning | Risk-ranked plan, resource allocation, approval, coverage | P0 | Sprint 5-6
EP-07 | Engagements | Setup, scope, team, milestones, status machine | P0 | Sprint 6-7
EP-08 | Audit Program | Procedure templates, risk/control mapping, customisation | P0 | Sprint 7-8
EP-09 | Workpapers | Testing, notes, samples, reviewer queue, sign-off | P0 | Sprint 8-10
EP-10 | Evidence | Secure storage, checksum, versions, access logging | P0 | Sprint 8-10
EP-11 | Findings | Finding lifecycle, severity, response, recommendation | P0 | Sprint 10-11
EP-12 | Remediation | CAPA, milestones, escalation, validation, closure | P0 | Sprint 11-12
EP-13 | Branch Audit | Branch checklists, risk grade, concurrent audit foundation | P0 | Sprint 10-12
EP-14 | Dashboards | CAE, Board, manager, branch dashboards | P0 | Sprint 12-13
EP-15 | Notifications | Tasks, reminders, SLA escalation | P0 | Sprint 12-13
EP-16 | Audit Trail | Immutable event model, search/export | P0 | Sprint 13
EP-17 | CBS Connector | One client CBS integration + reconciliation | P0 | Sprint 9-13
EP-18 | HRMS Connector | Employee/org feed + termination status | P0 | Sprint 11-13
EP-19 | CAAT Data Hub | Source registry, mapping, ingestion, data quality | P0 | Sprint 13-15
EP-20 | CAAT Rule Engine | Rule DSL/config, scheduler, exceptions | P0 | Sprint 15-17
EP-21 | CAAT Initial Library | First 20-30 rules from library above | P0 | Sprint 16-18
EP-22 | Exception Management | Triage, disposition, evidence, finding linkage | P0 | Sprint 17-18
EP-23 | Security/VAPT | SAST/DAST, access tests, VAPT remediation | P0 | Sprint 18-20
EP-24 | UAT & Deployment | UAT, migration, training, production readiness | P0 | Sprint 20-22
AI-01 | ML Data Pipeline | Feature store, training dataset, model registry | P1 | Post-MVP
AI-02 | Anomaly MVP | Isolation Forest/statistical baseline + scoring | P1 | Post-MVP
AI-03 | AI Alert UX | Explainability, disposition, feedback loop | P1 | Post-MVP
AI-04 | Peer Benchmarking | Peer grouping and deviation scores | P1 | Post-MVP
AI-05 | Entity Risk | Dynamic entity risk profile | P1 | Post-MVP
AI-06 | Model Monitoring | Drift/performance/false-positive dashboard | P1 | Post-MVP
AI-07 | GenAI Gateway | Private/enterprise LLM gateway + RAG controls | P2 | Phase 3
AI-08 | Audit Copilot | Planning, evidence summary, finding drafting, Q&A | P2 | Phase 3

## Screens
ID | Module | Screen | Purpose | Users | Priority
AUTH | Login | Email/employee ID, password/SSO, MFA, device/session policy. | All | P0
AUTH | MFA / Verification | OTP/app verification, trusted-device policy. | All | P0
HOME | Role Dashboard | Role-specific KPIs, tasks, alerts and shortcuts. | All | P0
ORG | Organisation Tree | Bank/region/branch/unit hierarchy. | Admin | P0
ORG | Users | User search, create, deactivate, role and scope assignment. | Admin | P0
ORG | Roles & Permissions | RBAC, data scopes, maker-checker policy. | Admin | P0
ORG | Audit Types & Templates | Configure branch, concurrent, thematic, IT, credit, AML etc. | Admin | P0
AU | Audit Universe | All auditable entities/processes/systems/products. | CAE/Manager | P0
AU | Universe Detail | Risk, controls, prior audits, findings, incidents, coverage. | CAE/Manager | P0
RISK | Risk Register | Risks, inherent/residual scores, owners and linked controls. | Risk/CAE | P0
RISK | Risk Assessment | Assessment questionnaire, scoring, evidence and approval. | Risk/CAE | P0
RISK | Risk Heatmap | Risk distribution by branch/process/category. | CAE/Board | P0
PLAN | Annual Audit Plan | Risk-ranked universe, proposed engagements, resources, timing. | CAE | P0
PLAN | Plan Approval | Review, comments, approve/reject and version history. | CAE/Board | P0
PLAN | Coverage Map | Risk coverage vs audit plan; gaps and stale assessments. | CAE | P0
ENG | Engagement Register | Search/filter all audits by status/type/branch/risk. | Manager | P0
ENG | Engagement Setup | Objective, scope, period, team, risks, controls, milestones. | Manager | P0
ENG | Audit Program | Procedures/test steps mapped to risks and controls. | Manager/Auditor | P0
FIELD | Workpaper Workspace | Procedure, test, sample, result, notes and reviewer status. | Auditor | P0
FIELD | Evidence Vault | Upload/view evidence, metadata, versions, checksum, access log. | Auditor/Reviewer | P0
FIELD | Sampling | Sample population, methodology, sample selection and testing. | Auditor | P1
FIELD | Review Queue | Reviewer comments, clearance, re-submit and sign-off. | Manager | P0
BRANCH | Branch Audit Workspace | Branch checklist, risk grade, exceptions and findings. | Auditor | P0
BRANCH | Concurrent Audit | Recurring assignments, periodic checks and escalation. | Concurrent Auditor | P1
FIND | Findings Register | Findings by severity/status/owner/due date. | All authorised | P0
FIND | Finding Detail | Condition, criteria, cause, consequence, recommendation, response. | Auditor/Manager | P0
FIND | Action Plan | Owner, milestones, due date, evidence and validation. | Owner/Reviewer | P0
FIND | Closure Validation | Evidence validation and close/reopen approval. | Manager/CAE | P0
RCM | Risk-Control Matrix | Risk → control → process → test → finding mapping. | Risk/CAE | P1
RCM | Control Library | Control objective, description, owner, frequency, key-control flag. | Risk/Compliance | P1
RCM | Control Testing | Design/operating effectiveness and test evidence. | Auditor/Risk | P1
COMP | Regulatory Obligation Register | Requirement, source, effective date, owner, applicability. | Compliance | P1
COMP | Compliance Assessment | Obligation testing, evidence, breach/exception and action. | Compliance | P1
CAAT | Data Sources | CBS/HRMS/LOS/ERP/payment source configuration. | CAAT Admin | P0
CAAT | Data Mapping | Source-to-canonical field mappings and validation results. | CAAT Admin | P0
CAAT | Rule Library | Rule definitions, thresholds, scope, severity and versioning. | CAAT Admin | P0
CAAT | Run Monitor | Scheduled/manual run status, volume, errors and reconciliation. | CAAT Admin | P0
CAAT | Exception Queue | Exceptions, reason, score, disposition and linked finding. | Auditor | P0
CAAT | Analytics Explorer | Filters, aggregation, drill-down and export. | Auditor/Analyst | P1
AI | AI Alert Queue | AI anomaly alerts, severity, explanation and disposition. | Auditor | P1/Premium
AI | Entity Risk Profile | Customer/account/user/branch risk history and signals. | Auditor/CAE | P1/Premium
AI | Peer Benchmarking | Peer groups, outliers and trend deviation. | CAE/Analyst | P1/Premium
AI | Model Registry | Models, versions, features, validation and approval. | Model Admin | P1/Premium
AI | Model Monitoring | Drift, performance, false positives and alert volumes. | Model Admin | P1/Premium
AI | AI Explainability | Top factors, baseline, peer comparison and source records. | Auditor | P1/Premium
AI | Audit Copilot | Secure RAG Q&A, planning and drafting assistant. | Auditor/CAE | P2/Premium
REPORT | CAE Dashboard | Plan progress, risk coverage, findings, overdue actions. | CAE | P0
REPORT | Board Dashboard | High-risk findings, top risks, overdue remediation and trends. | Board | P0
REPORT | Branch Dashboard | Branch risk grade, findings, exceptions and audit status. | Branch | P0
REPORT | CAAT/AI Dashboard | Exceptions, alert ageing, false positives, model metrics. | CAE/Analyst | P1
ADMIN | Workflow Config | Statuses, approval levels, escalation and SLA rules. | Admin | P0
ADMIN | Audit Trail | Immutable event search and export. | Admin/Security | P0
ADMIN | Integration Monitor | API jobs, ingestion health, errors and reconciliation. | Integration Admin | P0

## User Journeys
ID | Journey | Flow | Key Rule
UJ-01 | UJ-01 Annual Risk-Based Planning | CAE → Audit Universe → Risk Assessment → Risk Ranking → Proposed Plan → Resource Allocation → Board/Audit Committee Approval → Baseline Plan → Quarterly execution | Plan must show why each engagement was selected and which risks it covers.
UJ-02 | UJ-02 New Audit Engagement | Manager → Select approved plan item → Define objective/scope → Map risks/controls → Assign team → Generate audit program → Approve engagement → Fieldwork | No fieldwork before required planning approval.
UJ-03 | UJ-03 Auditor Fieldwork | Auditor → Open procedure → Select sample/full population → Perform test → Attach evidence → Record result → Create observation/finding → Submit → Reviewer | Every conclusion links to procedure and evidence.
UJ-04 | UJ-04 Finding to Closure | Auditor → Draft finding → Manager review → Issue → Process owner response → Action plan → Evidence → Validation → Close/Reopen | Critical findings trigger immediate escalation.
UJ-05 | UJ-05 CAAT Exception | Data job → Validate/reconcile → Execute rule → Create exception → Auditor triage → False positive/Investigate/Escalate → Finding if warranted | Exception must preserve source record and rule version.
UJ-06 | UJ-06 AI Anomaly | Data pipeline → Feature generation → Model scoring → Hybrid score → Alert → Explainability → Auditor disposition → Optional finding → Feedback dataset | AI is advisory; human approval is mandatory.
UJ-07 | UJ-07 Regulatory Compliance | Compliance owner → Add/update obligation → Map process/risk/control → Assessment → Evidence → Exception → Action plan → Validation → Close | Regulation version and effective date are retained.
UJ-08 | UJ-08 Board Reporting | System aggregates approved records → CAE reviews → Board dashboard/report → Drill-down to findings/risks → Export | Board users are read-only unless explicitly authorised.

## RBAC
Resource | Board/Audit Committee | CAE | Audit Manager | Auditor | Concurrent Auditor | Branch/Process Owner | Risk | Compliance | CAAT Analyst | Model Admin | System Admin
Dashboard | R | RW | RW | R | R | R | RW | RW | RW | RW | RW
Audit Universe | R | RW | RW | R | R | R | RW | R | R | R | A
Risk Assessment | R | A | RW | RW | R | R | RW | R | RW | R | A
Audit Plan | R | A | RW | R | R | R | R | R | R | R | A
Engagement | R | A | RW | RW | RW | R | R | R | R | R | A
Workpapers | R | A | RW | RW | RW | R | R | R | R | R | A
Evidence | R | A | RW | RW | RW | R | R | R | R | R | A
Findings | R | A | RW | RW | RW | RW | R | R | RW | R | A
Remediation | R | A | RW | R | R | RW | R | R | R | R | A
RCM | R | A | RW | RW | R | R | RW | RW | R | R | A
Compliance | R | A | R | R | R | R | R | RW | R | R | A
CAAT Rules | R | A | R | R | R | R | R | R | RW | R | A
CAAT Exceptions | R | A | RW | RW | RW | R | RW | R | RW | R | A
AI Alerts | R | A | RW | RW | RW | R | R | R | RW | RW | A
Model Registry | R | R | R | R | R | R | R | R | R | A | A
Configuration | R | A | R | R | R | R | R | R | R | RW | A
Audit Trail | R | R | R | R | R | R | R | R | R | R | A

## CAAT Rules
Code | Rule | Logic Summary | Domain | Priority
CAAT-001 | Duplicate transaction | Same account/amount/type/date/time-window repeated beyond configurable tolerance. | Transactions | P0
CAAT-002 | Near-duplicate transaction | Same source/target/amount within short interval with differing reference. | Transactions | P0
CAAT-003 | Round amount anomaly | High-value round-number transactions outside normal profile. | Transactions | P0
CAAT-004 | Odd-hour transaction | Transaction outside branch/user normal operating profile. | Transactions | P0
CAAT-005 | Rapid in/out | Large credit followed by rapid debit within configurable window. | Deposits | P0
CAAT-006 | Dormant activation | Dormant account activated and high-value activity occurs shortly after. | Deposits | P0
CAAT-007 | Threshold splitting | Multiple transactions structured below a threshold. | AML/Cash | P0
CAAT-008 | Excessive reversals | User/branch reversal rate materially above peer baseline. | Operations | P0
CAAT-009 | Manual GL entry | Manual journal outside approved user/process profile. | GL | P0
CAAT-010 | Backdated GL | Posting date materially earlier than entry date. | GL | P0
CAAT-011 | Period-end spike | Unusual manual journals close to month/quarter/year end. | GL | P0
CAAT-012 | Suspense ageing | Suspense entries older than configured SLA. | GL | P0
CAAT-013 | User-role mismatch | Transaction type/limit inconsistent with employee role. | Access | P0
CAAT-014 | Terminated employee activity | Transactions after HR termination date. | Access | P0
CAAT-015 | Privileged-user anomaly | Privileged user performs unusual financial activity. | Access | P1
CAAT-016 | Maker-checker conflict | Same user or prohibited relationship performs both steps. | Access | P0
CAAT-017 | Duplicate beneficiary | Many accounts using same unusual beneficiary/account. | Payments | P1
CAAT-018 | High-risk beneficiary change | Beneficiary changed shortly before high-value transfer. | Payments | P1
CAAT-019 | Failed-payment pattern | Repeated failed/returned payments linked to unusual entity/user. | Payments | P1
CAAT-020 | Unusual branch fee reversal | Branch/user fee reversals above peer baseline. | Branch | P0
CAAT-021 | Cashier outlier | Teller transaction distribution differs materially from peers. | Cash | P1
CAAT-022 | Cash threshold pattern | Cash transactions clustered below reporting/approval thresholds. | Cash | P0
CAAT-023 | Loan disbursement before approval | Disbursement timestamp precedes required approval. | Loans | P0
CAAT-024 | Loan override concentration | Unusual concentration of overrides by user/branch. | Loans | P1
CAAT-025 | Restructuring repeat | Repeated restructuring patterns outside policy profile. | Loans | P1
CAAT-026 | Write-off anomaly | Write-offs materially above peer/product baseline. | Loans | P1
CAAT-027 | Overdue escalation gap | Loan reaches configured delinquency stage without expected action. | Loans | P1
CAAT-028 | Employee-vendor overlap | Employee identifiers/contact/bank details overlap with vendor. | Procurement | P1
CAAT-029 | Invoice duplicate | Duplicate or near-duplicate invoice/vendor/amount/date. | Procurement | P0
CAAT-030 | Split procurement | Multiple purchases from same vendor below approval threshold. | Procurement | P1
CAAT-031 | Ghost payroll indicator | Salary payment without active HR record or expected attributes. | Payroll | P0
CAAT-032 | Salary outlier | Unusual salary change or allowance compared with employee history/peer group. | Payroll | P1
CAAT-033 | Trade amendment anomaly | Repeated amendments/manual overrides outside product baseline. | Trade | P1
CAAT-034 | Missing approval | Required approval absent from transaction lifecycle. | Operations | P0
CAAT-035 | Branch peer deviation | Branch KPI/transaction distribution materially differs from peer group. | Branch | P1
CAAT-036 | Repeat finding exposure | Universe item has repeated findings within defined period. | Audit | P0
CAAT-037 | Overdue action concentration | Owner/unit has materially elevated overdue remediation. | Audit | P0
CAAT-038 | High-risk control not tested | Key/high-risk control has no current test. | Controls | P0
CAAT-039 | Data quality exception | Source totals/counts fail reconciliation or completeness checks. | Data | P0
CAAT-040 | Unusual customer/account network | Entity participates in unusually dense or circular transaction relationships. | Network | P2

## API
Domain | Method | Endpoint | Purpose | Priority
Auth | POST | /api/v1/auth/login | Authenticate or initiate SSO flow | P0
Users | GET/POST | /api/v1/users | List/create users | P0
Roles | GET/POST | /api/v1/roles | Manage roles/permissions | P0
Universe | GET/POST | /api/v1/audit-universe | List/create universe items | P0
Risk | GET/POST | /api/v1/risks | Risk register | P0
Risk | POST | /api/v1/risks/{id}/assessments | Create risk assessment | P0
Planning | GET/POST | /api/v1/audit-plans | Create/list audit plans | P0
Planning | POST | /api/v1/audit-plans/{id}/submit | Submit for approval | P0
Planning | POST | /api/v1/audit-plans/{id}/approve | Approve plan | P0
Engagement | POST | /api/v1/engagements | Create engagement | P0
Engagement | GET/PATCH | /api/v1/engagements/{id} | Read/update engagement | P0
Procedures | GET/POST | /api/v1/engagements/{id}/procedures | Audit procedures | P0
Workpapers | GET/POST | /api/v1/workpapers | Workpapers | P0
Evidence | POST | /api/v1/evidence/presign | Secure upload URL/handshake | P0
Findings | GET/POST | /api/v1/findings | Findings register | P0
Findings | POST | /api/v1/findings/{id}/issue | Issue finding | P0
Actions | GET/PATCH | /api/v1/action-plans/{id} | Remediation status | P0
CAAT | GET/POST | /api/v1/caat/sources | Data sources | P0
CAAT | GET/POST | /api/v1/caat/rules | Rule library | P0
CAAT | POST | /api/v1/caat/runs | Start rule run | P0
CAAT | GET | /api/v1/caat/runs/{id} | Run status/results | P0
CAAT | GET | /api/v1/caat/exceptions | Exception queue | P0
AI | POST | /api/v1/ai/scoring/jobs | Start model scoring job | P1
AI | GET | /api/v1/ai/alerts | AI alert queue | P1
AI | POST | /api/v1/ai/alerts/{id}/disposition | Human disposition | P1
AI | GET | /api/v1/ai/models | Model registry | P1
AI | POST | /api/v1/ai/models/{id}/deploy | Deploy approved model | P1
Reports | GET | /api/v1/reports/dashboard | Dashboard data | P0
Audit Trail | GET | /api/v1/audit-log | Authorised event search | P0

## Entities
Entity | Key Fields / Purpose
organisation | id, parent_id, type, code, name, status
user | id, employee_id, name, email, status, org_unit_id
role_permission | role_id, permission_id, action, resource, scope
audit_universe_item | id, type, parent_id, owner, risk_profile, audit_frequency
risk | id, statement, category, owner, inherent_score, residual_score
risk_assessment | risk_id, period, factors, score, methodology_version, approval
control | id, objective, description, owner, frequency, key_control
control_test | control_id, engagement_id, result, evidence_id, effectiveness
audit_plan | id, period, version, status, approved_by
audit_plan_item | plan_id, universe_item_id, risk_score, proposed_period, effort
engagement | id, plan_item_id, type, objective, scope, dates, status
audit_procedure | engagement_id, risk_id, control_id, procedure, result
workpaper | procedure_id, version, content, review_status, signoff
evidence | workpaper_id, object_uri, checksum, source, classification
finding | engagement_id, severity, condition, criteria, cause, consequence, recommendation, status
action_plan | finding_id, owner, due_date, milestones, status
regulatory_obligation | source, reference, issue_date, effective_date, text, owner
data_source | system, connection_type, schema_version, refresh_frequency
data_mapping | source_field, canonical_field, transform, validation_rule
caat_rule | rule_code, expression, scope, severity, version, active
caat_run | rule_id, start/end, row_count, exception_count, status
caat_exception | run_id, source_key, reason, severity, disposition
ai_model_version | model_id, algorithm, training_period, features, threshold, approval
ai_alert | model_version, entity_type, entity_id, score, explanation, status
ai_disposition | alert_id, disposition, reviewer, reason, finding_id
audit_log | actor, action, object_type/id, before_hash, after_hash, timestamp

## Architecture
Layer | Recommended Approach
Frontend | React/Next.js or equivalent enterprise SPA; responsive component library.
Backend | Modular service-oriented backend; REST/JSON; API-first.
Transactional DB | PostgreSQL or equivalent enterprise RDBMS.
Analytics | Separate warehouse/lakehouse/columnar store for CAAT.
Object Storage | Encrypted versioned object storage for evidence.
Queue | Kafka/RabbitMQ/SQS-equivalent for ingestion and async jobs.
ML | Python services; scikit-learn/PyTorch; model registry.
GenAI | Provider-agnostic private/enterprise LLM gateway + RAG.
Identity | OIDC/SAML SSO, MFA, RBAC.
Deployment | On-premise/private cloud/managed cloud; containerised.

## AI Roadmap
Feature | Tier | Purpose
Rules-based CAAT | Core CAAT | Transparent automated tests.
Statistical baselines | Premium | Peer and historical deviation.
Unsupervised anomaly detection | Premium | Unknown pattern detection.
Entity risk scoring | Premium | Dynamic risk prioritisation.
Peer benchmarking | Premium | Branch/user/process outliers.
Predictive repeat-finding risk | Premium | Prioritise remediation/follow-up.
Continuous assurance | Premium | Daily/near-real-time monitoring.
GenAI Audit Copilot | Premium+ | Planning, summarisation, drafting, Q&A.